## RTL Reflection and Action Plan
Key Terms | Overall Recommendations from Interviewed Stakeholders | Management Reflections | Follow Up Action | Responsible person / team | Expected Deadline
NSD Support | Support for financial sustainability, business continuity and income-generating activities | The NS financial sustainability component of the appeal remains vague - "establishment of reliable financial mechanisms and sustainable long-term domestic fundraising bases, strategies, plans and their execution" . While we agree that this is an overarching goal, we should focus on 1 or 2 clear outputs, agreed with the NS, and budget for accordingly in NS plans. | NSD and Operations team to work closely with NS to define what are the concrete, realistic financial sustainability steps that can be achieves in 2021, i.e. develop/strengthen one income source; develop a domestic fundraising plan, conduct a review of the NS HR base, etc. specially in fragile contexts such as DRC, Somalia, South Sudan etc. | NSD | 2021-01-01
Support for financial sustainability, business continuity and income-generating activities
| Improving the wellbeing of volunteers | Volunteer wellbeing is derived from their legal, enterprise and social safeguards, which are set up by each national society. At the very minimum, every volunteer should be insured (either through insurance company or a fund), should be able to reach out to their branch and receive an appropriate answer, and have appropriate psychosocial services. | "Volunteers have access to insurance or a fund that will replace this insurance, in case they fall ill or suffer while on duty A feedback mechanisms is established so that volunteers can raise their concerns/suggestions and appropriate answers are given PSS services are made available to volunteers (internally or outsourced All of the above should be budgeted in NS PoAs" | NSD/Operations | 2021-03-01
| Strengthening National Societies capacities in technical areas (including livelihoods, PMER, Comms) | It is up to National Societies to define the technical areas they wish to invest, noting that this would come at a cost to National Societies, including extra human and financial resources. We should discourage National Societies having one technical focal point that is involved in capcity building initiatives in many different areas (as it often happens). An adequate capacity building plan, and NS commitment is required. Streamlining the CB offer accross different NS partners, IFRC and ICRC is paramount. | At this stage, 24 National Societies have engaged in CB for Cash & Voucher programming. This should remain the priority.Other technical support should be incorporated in their PoAs, and budgeted for accordingly
| Adaptation to remote work and online trainings. | "Take advantage of the COVID-19 budget to cover partially the NS hardware needs - renewing IT equipment and internet infrastructure. Reduce the intensity of online trainings, and be critical about those that are of relevance to NS. " | NSD and IT teams to reach out to NS that need support, and suggest an appropriate system for remote working, with a budget attached. | NSD/IT | 2021-02-01
| National Societies learn from each other (peer support between National Societies) | There are limited spaces for NS exchange of information | Strengthen/revitalize the sub-regional networks for NS exchange, supported by the IFRC clusters. | Operations teams/Cluster Offices | 2021-03-01
Needs-based | Allocations need to be driven by needs, not by the National Society's capacity to spend | Encourage head of country to be ambitious and to seek opportunities to scale |  |  | 2021-03-01
| Strengthen National Society consultation process |  | NS consultations are defined differently by country reps. And we need to better define the expcectations we have. |  | 2021-03-01
| Flexibility and agility to changing needs |  | Constant monitoring and engagament is needed. Early warning mechanisms to course adjust. |  | Ongoing
| Focus on what National Societies need to be sustainable |  | This is the make or break top engagment for many NSs - needing a global and regionally aligned engagement in RM |  | Ongoing
| Earmarking must be aligned with needs |  | Continued and more intense HD efforts and advocay to address critical gaps and priority groups. |  | Ongoing
Demands and expectations | Managing expectations based on available/expected funding | Share insight of funding and gaps with relevant staff to create HD momentum
| Better engagement with donors to increase buy-in in overall plan and reduce earmarking | Huge task and priority for 2021 at regional and country levels and with NS partners; create joint narrative including NSD and IO
| National Societies need clear and timely guidelines/technical advice | Engage with NS to appreciate priorities and communicate opportunities. make use of virtual scalable solutions
| Perception that all major decisions have been made in Geneva secretariat - blur between strategic and operational leadership | Clarify that we are in process of transformation and that tactical and operational decisions increasingly will be managed by CCO
| Additional HR support needed for units/teams that are overwhelmed | Better engagement with donors to increase buy-in in overall plan and reduce earmarking
Evidence-based and risk-informed | Reducing bureaucracy so funds can get to the country-level faster | Listen to country manager's experience and build solutions with finance and HR teams - bottom up. This is urgent
| Closely monitoring local context, National Society needs and gaps, absorption capacity, socio-economic impact, etc. | NS plans build on stong situational analysis, comparative advantage, understanding of donor environment, co-create with donors to incease changes of success
| Clear criteria and decision-making process for funding allocation | Combination of performanced based investment and absorption capacity
| Stronger consultation process with National Societies | Support NS to lead coordination and build it around NSD plan and country niche
Strong risk management | Acknowledging the complexity and dynamic context of the situation and establishing a flexible approach that increases agility
| Closely monitoring National Society implementation capacity | At the risk management level, it is necessary to strengthen the risk management culture at all levels of the organization, as well as to create a global risk management framework that allows risk management to be included in operations. This framework should be based on the three lines of defence, so it should include National Societies and the design and implementation of key risk indicators, as well as levels of risk reporting for decision-making. In some regions there is already a Risk Management Office that is helping countries and cluster offices to identify risks in operations and define action plans to mitigate these risks. The Partnership model needs to reflect IFRC models. NS monitoring can be based on recent programmatic implementation history, including reporting and financial validation. There is not yet a clear KPI system in place. The IFRC silo approach can affect the work with NS’s. Existing Frameworks OCAC / BOCA – only 1NS certified (Costa Rica) and 1 in process (El Salvador) PER (Preparedness for Effective Response). PNS supporting Well Prepared National Society (WPNS) transformed Further monitoring frameworks needed in HR – Logistics - RM Communications development - PMER All should be under an NSD developed framework. We still monitor in classic terms and manners – through programmatic KPIs, baselines and impact of the funding invested (by PNSs, IFRC and sometimes ICRC) Current long term processes: National Society Development Framework 2013 National Society Development Framework Brochure 2013 National Society Development Compact 2019 The Aim of National Society Development Urgent need for Volunteer services development (protection, insurance, training, volunteer promotion, etc) Processes: NS Governance Finance Sustainability Compact – needs engagement of several units PSK, Finance, PRD and the leadership Need to agree with all NS on what and how we monitor, and permission to monitor. Reputational risk with NS: lack of knowledge of the Rules, regulations and internal processes, Monitoring should be accompanied by reporting and by good management. | Define the general guidelines and standard tools for risk management at a global level. Define a long-term risk management culture plan Design and implement key risk indicators that include the absorption capacity of National Societies Design risk management reports with their frequency and levels of reception and escalation Maintain and update the risk register, security risk register and contingency plans. Prioritize current tools for National Society Development. Systematic promotion and support of Volunteer development throughout the region Retention of trained staff at the Secretariat level and at the NS level. Support NSD at the regional level, supporting NSD plan for the Americas and NSD strategy. Review possibility to develop KPI’s to indicate NS capacity to implement funds/ activities. Establish NS thresholds for advances respective to risk analysis. Work on a consolidated PSK/NS Capacity development plan Link OCAC, WWPP, Evaluations, Monitoring reports, and any other NS reports. Localize resources. Review of investment decisions | Leadership & PSK Task force for NS with all units.
| Planning ahead, including for the incorporation of COVID-19 activities into programmes when funding runs out. | 4/2021 – 5 year period Revising the concept of long-term planning when we do an exercise that is conceived for 12 months only. Integrating COVID 19 will be the new norm – it should be integrated as soon as possible. A high percentage of COVID 19 pledges are ending by March 2021 (in the next 4 to 5 months). A high percentage of the EAs are related to sudden onset events and pandemics. The current funding relationship is difficult to develop and base on planning, as the nature of Emergency Appeals is urgent. Invest in PRD, Finance and PMER to work on the incorporation. Socializing the Agenda for Renewal and what are the specific actions, to be closer to the Membership, co-creating and with one resource mobilization plan per Country plan / cluster plan – embracing the National Societies. | Start dialogue from HoCO and HoCCST with the NSs and the membership to build one Resource Mobilization plan – support from PRD ARO and PRD GVA, roll out of RM strategy and support to the NS on the RM plans. Based on the Strategy 2030 roll out, create long term plans with the membership (4 to 5 years). Build a plan to integrate COVID related activities into the thematic programmes for 2022 onwards; build funding plans and proposals to donors including those activities. | Leadership – HoCO & HoCCST – PMER, Finance and PRD | 2021-06-01
| Putting aside funds for unexpected large-scale events. | Review DREF Recovery funding is not well supported. COVID effects on NS’s annual budget is extensive and continues. Federation Wide Resource Strategy (with COVID 19 components) – currently being done. More effort is needed in: Movement Wide Resource Mobilization campaigns and visibility Multilateral and Finance Institutions. Individual donations / crowdfunding Social media promotions Digital fundraising Private sector engagement. Increase communications Unearmarked funding DAG potential PRD capacity in IFRC and NS’s Take advantage of the agenda for renewal roll out. All offices to support building alliances with the private sector Main challenges for fundraising are in mid-size events and for NSD. | CO/CCST work on RM strategy at country level. Develop one overall RM plan with NS’, membership, and GVA PRD support for regional plan. Increase PRD resources at cluster and country level. Train staff in Agenda for Renewal, rules of engagement and co-creation work with the membership. Allocate emergency funding for NS development. (1%) | Leadership – HoCO & HoCCST –PRD – with all the other units | 2021-06-01