Lessons Learned Review: OCHA-Angola 2000 – 2002

# A. Introduction

- As part of its commitment to improving its performance, OCHA has undertaken a Lessons Learned review of its work in Angola, focusing on the years 2000-2002.    This period has been chosen because it was one of tremendous humanitarian crisis, during which OCHA-Angola responded by engaging robustly with all partners, and by introducing a number of innovations to coordination.  This robust, innovative approach, described as “full coordination,” is the focus of the Lessons Learned review.

- This report assumes some familiarity with the conflict in Angola.  During the course of the war – which began in 1974 and ended definitively in 2002 -- millions of civilians suffered displacement, death by malnutrition and long periods under siege in provincial capitals.   The humanitarian response to this protracted crisis was massive.  By 2000, 10 United Nations (UN) Agencies, 80 international Non Governmental Organisations (NGOs), 300 National NGOs, and numerous Government bodies were all engaged in humanitarian response.  This was OCHA-Angola’s constituency, in a country of 1.2 million square kilometers and more than 13 million people.

- OCHA first established a presence in Angola in 1993.  In the ensuing period an array of coordination mechanisms and an extensive field structure were established.  These were the building blocks for OCHA-Angola 2000-2002.  OCHA’s long tenure in the country is of singular importance.  The seven years work – and accrued reputation – that preceded the review period put OHCA-Angola is a position to take the assertive steps of 2000-2002.

# B. Methodology and Report Structure

- Research for the Lessons Learned Review was primarily undertaken through interviews carried out in Angola from 9 – 22 August 2003.  This report is not exhaustive.  OCHA-Angola is a repository of guidelines for implementing most facets of coordination.  As such a thorough recording of OCHA-Angola’s best practices should be undertaken as a priority, in order to augment existing instruction for OCHA field offices.  Priority here has been given to generic lessons of the period under review that were noted by OCHA-Angola staff and their partners in the field.  Two broad and related areas will be addressed in some detail:

    - The Coordination Process – Planning, Coordination Mechanisms, Information Management and Field Presence.

    - Innovations in Coordination – Normative or Standard Setting Activity, Protection, Emergency Response Funding and Leadership.

- The report concludes by proposing a single, principal lesson of OCHA-Angola’s 2000-2002 experience.

# C. The Coordination Process

i. Planning - The more inclusive the planning process, the more effective the coordination.

### Summary

- Developing humanitarian strategy in Angola was a shared affair.  Each step in the planning process increased consensus through inclusion of all relevant actors and the use of transparent ground rules.  OCHA-Angola, as the coordinating body, drove this process by convening and managing all major planning fora, and by finalising, disseminating and then supporting the application of protocols and guidance for the full planning cycle – from assessment through to monitoring.  The end result was that all major stakeholders agreed to a set of priorities, arrived at through the use of clear methodologies, which were designed and supported by OCHA-Angola.  This planning process was so inclusive that it became ‘the only game in town,’ and the opportunity cost of abstaining became prohibitive for serious humanitarian organisations.

### Detail

- The planning process in Angola began with shared assessments based on common guidelines prepared by OCHA-Angola in collaboration with relevant partners.  These assessments were undertaken jointly by a cross-section of the humanitarian community and were facilitated by OCHA-Angola.  Once recorded, these joint assessment findings were discussed at the national level, through a series of meetings convened by OCHA-Angola on behalf of the Government. These discussions identified priorities.  Nationally agreed priorities were then adopted at the provincial level, where plans were developed under Government auspices, facilitated by OCHA-Angola.  These provincial plans became the basis for the annual Consolidated Appeal.  The inclusion of Government in most processes, in a titular leadership role also reflects OCHA-Angola’s commitment to including a capacity building element into their activities wherever possible.

- The planning process in Angola also reflected a strong understanding of context, reflected by pragmatic adjustments of approach.  In 2000 and 2001 for example, the nature of the conflict required extremely rapid assessments of large-scale displacement and immediate response to emergency needs.  Planning tools were appropriately tailored by establishing procedures that required assessment findings to be transformed into Plans of Action within twenty-four hours, specifying needs in four designated ‘Core Pipeline’ areas.  In 2002, as the war concluded, the need for rapid action continued, but those most in need were to be found in small pockets throughout the country rather than in large groups of displaced.  Assessment protocols were again adjusted to ensure that they best addressed this situation.

- Inclusive planning required more than clear methodologies and pragmatism.  OCHA-Angola also engaged in tactical management of different constituencies.  The humanitarian community in Angola divided into a series of natural groups: UN Agencies, International and National NGOs, donors and Government, or combinations thereof.  These groups sub-divided further (a distinction could be drawn for example, between the discussions at the technical and management levels).  Each of these different constituencies was engaged separately throughout the planning process (see “Coordination Mechanisms”).  While priorities and goals were consistent across groups, emphasis or presentation was altered as required to ensure buy-in from each member of a diverse community.  OCHA-Angola also recognized a clear hierarchy of partners.  Every effort was made to secure the support of major donors, certain UN Agencies and the Government as a matter of priority, with the understanding that agreement from major enablers and potential spoilers was a requirement of moving forward.

- The results of this inclusive planning are best reflected in participation in the Consolidated Appeals Process (CAP).  All major humanitarian actors (save the churches) participate in the CAP.  Many of the NGOs did so acknowledging that participation had no relationship to funding flows.  Despite its not bringing in any money, the CAP was seen as “the only game in town,” an opportunity to have a hand in setting priorities, and an opportunity to illustrate their engagement in the planning process to donors.  The Government showed similar commitment.  In one case (Huile Province) using the CAP to monitor the humanitarian programme.

# ii. Coordination Mechanisms – Complementary coordination mechanisms unify a diverse humanitarian community and strengthen coordination.

### Summary

- OCHA-Angola convened and serviced such a wide range of coordination mechanisms (meetings, seminars, ad hoc and issue specific discussions) that all humanitarian actors of relevance were drawn into the coordination process.  Coordination mechanisms were convened in the provinces and at the national level, and covered all manner of issues, ranging from the technical (e.g. sectoral priorities for an emergency response) to the “political” (addressing group concerns over Government action).  This saturation tactic enhanced coordination by allowing OCHA-Angola to deliver a consistent message on strategic priorities to the entire humanitarian community through these numerous meetings, helping to set the direction for the humanitarian programme.

### Detail

- During the more intense periods of crisis between 2000 and 2002, OCHA-Angola convened 80 coordination fora per week countrywide.  Meetings and discussions occurred at all levels and on an enormous range of issues.  Despite this necessary diversity each coordination mechanism promoted the same strategic objectives.  This was possible because OCHA-Angola was in the unique position of having regular contact with the different elements of the humanitarian community, which allowed them to obtain an overview of the prevailing situation, identify themes and build consensus around approaches to problems.

- A variation on this approach was also applied to relations with the UN Country Team (UNCT).  As a result of unequivocal support for OCHA-Angola from the UN Humanitarian and Resident Coordinator, and the full and forceful participation of the OCHA Angola Head of Office in UNCT meetings OCHA was able to lead a process of setting global humanitarian priorities within the UNCT.  This occasionally caused disquiet within UN agencies, where some UNCT members believed OCHA was setting priorities where they should have been ‘servicing’ the UNCT.

- OCHA-Angola also used coordination mechanisms to establish unconventional coalitions for humanitarian planning.  The best such example of this organisational pragmatism was probable the Technical Team, a grouping of UN Agencies and major NGOs who met regularly at the technical level to discuss a range of issues and establish planning frameworks and operational priorities.  This group was convened under OCHA’s chairmanship and met the day before the UNCT.  This allowed for the development of proposals at the technical level, by an extended sample of the humanitarian community, for consideration by senior UN staff.

- Because they were so assiduous in convening and facilitating coordination mechanisms, OCHA-Angola provided platforms for group action where they otherwise may not have existed in any systematic way.  This group action often took the form of a demarche to Government regarding policy.  Different humanitarian organizations were able to discuss the impact of Government policy at an OCHA convened forum, agree the most productive reaction and present it to the Government en groupe, giving the demarche significantly more weight than if it had been made bilaterally or by an ad hoc coalition.

- While humanitarian organizations saw the different coordination mechanisms as opportunities to have influence and engage in planning, OCHA-Angola kept participants engaged by providing information and analysis that they may otherwise not have been able to access.   Through their national network of field offices (see section C.iv below), their relationship with Government or with the donor community, OCHA consistently provided different constituencies with an overview that may have otherwise been beyond their capacity, or accessed information that may have been beyond their normal scope (see section C.iii below).

- OCHA-Angola also put great emphasis on the importance of setting a very high standard for preparation for each meeting, seminar or discussion group.  The quality of OCHA-Angola’s information products, the responsiveness to queries and requests and the efficiency with which meetings were managed gave OCHA-Angola a certain stature and reputation for professionalism that encouraged partners to participate in coordination mechanisms.

iii. Information Management – High quality information and analysis is the basis for humanitarian strategy.

Summary

- OCHA-Angola’s capacity to collect and broadly analyse humanitarian information was un-matched.  Their network of field offices provided information from the country’s most conflict-affected zones; and their coordination mandate allowed them to collect information in all sectors, as well as in some non-technical areas that were critical to humanitarian programmes (including security and access).  OCHA-Angola analysed this information, spotting trends and patterns and establishing the parameters for humanitarian planning and action.  Consistently high production values, characterised by the timeliness and readability of outputs, gave OCHA’s analysis even more weight with humanitarian community.

Detail

- During the period under review OCHA-Angola was the principal source for regularly available information on humanitarian matters.  A national network of field offices allowed for unparalleled reach in information collection.   Those organizations that had comparable field structures were focused on collecting information relating to their sector of activity.  OCHA-Angola, as the coordinating entity with no predominant sectoral responsibility, provided a multi-sectoral analysis of the humanitarian situation across the country.  This comprehensive view became the natural baseline for developing strategies.  OCHA’s information, in many ways shaped discussion within the humanitarian community.

- OCHA-Angola performed an additional essential service by collecting, analyzing and disseminating information on matters like security and access.  These non-technical issues were critical to humanitarian work, but were not addressed in a comprehensive fashion by agencies with sector-specific mandates for use by the wider humanitarian community.

- OCHA-Angola’s information collection capacity was complemented by its analysis and packaging of information.  A wide range of information products were made available to partners, ranging from the standard situation report to elaborate province-specific briefing packages for visiting delegations.  On balance information products that provided analysis, identification of trends and an overview of the humanitarian situation were better received than operational documents, whose focus on real-time facts and figures meant that they were quickly out of date and frequently manipulated by National media.

- The unique role and wide readership of OCHA-Angola’s information materials meant high standards were essential for all outputs, with a premium being put on clarity of language, professionalism of presentation and rapid turn-around time.  Reports and other documents were produced in small teams, with information and policy or field staff collaborating to produce a draft.  Given the standards set by the office, the onus for finalising documents  inevitably rested with English mother-tongue staff.  For example, nothing was released for public consumption until it had been cleared by the Head of Office.  The inefficiencies of this system notwithstanding, its vigour created a high level of confidence within the humanitarian community regarding OCHA-Angola’s outputs.  So much so that some major donors often forwarded OCHA reports to their capitals without comment or annotation.

iv. Field Presence – A national network of field offices staffed by experienced humanitarians is an essential component of effective coordination.

### Summary

- Field offices in key administrative and population centres outside the capital were at the heart of OCHA-Angola’s success.  By acting as the conduit for humanitarian information to the capital from the provinces and again in the other direction, the field offices informed national-level planning while keeping provincial approaches consistent with those set centrally.  Their role as information hub and the link to a nation-wide humanitarian constituency also made them the logical local liaison with the Government on humanitarian matters.  This representational role, and general relevance to humanitarian actors was further enhanced by Field Advisers’ responsibility to determine the prevailing security situation in their area of concern.

### Detail

- OCHA-Angola’s field network was among the most extensive within the humanitarian community in Angola.  As with the central level, the OCHA-Angola offices in 11 provincial capitals became the hub for planning in the field.  This planning function began with information flows, which occurred in three directions.  First, information moved from actors in the provinces to OCHA-Angola field offices.  By collecting their own information, receiving some from other agencies and then sharing what they had (through different information products or coordination mechanisms), OCHA-Angola field offices provided a critical service for partners and were the locus for an up-to-date picture of needs in the provinces, and also of who was doing what where.  This work allowed for field-level prioritization and crisis management.  Second, information moved from the provinces to the Luanda level to support development of national strategies.  Third, information moved from the national level back out to the provinces.  This put provincial work in a national context.  As a result OCHA-Angola field offices were imbued with a certain legitimacy, as the source of a higher order of information than most provincial actors would be able to access.  Similarly, OCHA-Angola also briefed, facilitated or hosted the majority of international delegations’ visits to the provinces. This cemented the perception of OCHA-Angola’s legitimacy in the field.

- As the provincial locus for information and planning, OCHA-Angola’s field offices were the humanitarian community’s principal liaison with local officials.  This liaison work increased the awareness and sensitivity of local authorities to their obligations, as well as to the role played by humanitarian organizations.  National NGOs, whose access to authorities was limited, benefited particularly from OCHA’s representation work.  In a parallel development, OCHA-Angola field staff, with a sound understanding of the situation in their province of concern and good links to Luanda, developed a ‘good offices’ function, providing input to and the venue for discussion of contentious issues, or crisis management.

- OCHA-Angola’s responsibility for determining the field-security situation also strengthened coordination.   The wider community accepted the logic of OCHA-Angola performing this function, which focused on the developments in the conflict and the status of mined roads.  The Field Adviser was seen to have the best overview of information, and would not be vulnerable – as a coordinator -- to the pressure that staff from an operational agency might experience.  In addition to addressing the safety concerns of the humanitarian community, OCHA-Angola’s involvement in field security required regular contact between Field Advisers and high ranking military and security personnel in the provinces.  These relationships, which other humanitarians did not have the opportunity to establish, afforded OCHA considerable advocacy opportunities.

- Managing OCHA-Angola’s field offices was a challenge in a country as large and geographically diverse as Angola.  Nevertheless, a certain consistency of approach was required from each of the provinces to be able to develop a rational national plan.  This consistency was achieved largely by setting basic, centralized planning requirements – revolving around the production of provincial plans and the CAP and maintained through regular reporting requirements.  These benchmarks were complemented by a kind of “maximum management,” which had Luanda in nearly daily contact with Field Advisers during intense periods of work and included regular visits to the field from management.  There were limits to what Luanda could do however.  Perhaps realising this, Field Advisers were encouraged to seek local solutions whenever possible.  When support on matters of policy or organisational politics were required, Luanda provided full backing.   Delivering operational support (provision of equipment, or repair of vehicles for instance) was more difficult and took more time.  This was probably related in part to OCHA-Angola’s dependence on UNDP administration and also on difficulties intrinsic to logistics in a country the size of Angola.

# D. Innovations in Coordination

- During the period under review, the coordination process – in all its constituent parts – created a powerful momentum for OCHA Angola.  Manifested and reinforced by the support of the humanitarian community, useful relations with Government, an unparalleled field presence and information gathering capacity, OCHA-Angola worked to develop this momentum by creatively introducing thereto unconventional  coordination measures.  A number of these are addressed in this section.

i. Normative and Standard Setting Activity: Establishment of the Norms and Regulamento - Change-making advocacy requires an enforceable legal framework, which can be created through diligent collaboration with Government.

### Summary

- Large numbers of Angolans were displaced during the conflict.  Government showed little concern for the international norms regarding treatment of these internally displaced persons (IDPs).  OCHA-Angola recognised that the most meaningful standard for treatment of IDPs was a national one, where internationally recognised standards could be established in domestic legislation.  To do so, OCHA-Angola drafted legislation for the Government (the Norms) based on the Guiding Principles on Internal Displacement, and operational guidelines for humanitarian organisations (regulamento) based on SPHERE standards.  The Government eventually adopted both.  The entire process took more than two years and required sustained contact with Government.  Including and especially those officials who were deemed to be sympathetic to the idea.

### Detail

- In 2000, the humanitarian community in Angola faced the large-scale forced displacement of civilians by Government and the outstanding needs of those already displaced.  The Government plan called for re-settlement of civilians beyond the army’s lines of defence – or what amounted to ‘human-shield’ tactics.  To make this plan work Government required the humanitarians help in providing for the resettled.  Objections from the humanitarians and invocation of International Humanitarian Law (IHL) or International Human Rights Instruments did not convince the Government to change their plans.  Internationally recognised humanitarian standards (e.g. SPHERE) were equally meaningless in lobbying the Government.  With resettlement continuing and discussions with Government at an impasse, OCHA-Angola determined that a legal framework was required that would allow beneficiaries to understand their rights (to remain in their homes, or to be provided for if force majeure required movement) while also giving humanitarians a robust platform for arguing them.

- In development this legal framework, OCHA-Angola recognised that the Government showed little regard for IHL and International Human Rights instruments.  In the provinces this disregard for (or misunderstanding of) internationally defined obligations was even more pronounced.  Only a national law would provide an irrefutable basis for insisting on change.

- OCHA-Angola took four related steps to address the crisis.  First, they collaborated with other humanitarian organisations to define “minimum operating standards” that would set the ground rules for humanitarians’ support of resettlement activities.  There ground rules would allow for immediate action.

- Second, OCHA-Angola initiated a dialogue with technical level staff within the Government of Angola on the need to establish fixed and official standards for resettlement – derived from the “minimum operating standards” identified by the humanitarian community..  The point of departure for these preliminary discussions was the Guiding Principles on Internal Displacement of the UN Secretary-General’s Special Representative on IDPs.  In what turned out to be a prescient action, OCHA had translated the Guiding Principles into Portuguese in 1998 and over the years had referred to them regularly in discussions with partners.

- Third, OCHA-Angola provided the Government with draft legislation that would establish the Guiding Principles as national law in the form of Norms on the Resettlement of Internally Displaced [sic].

- Fourth, when language for the Norms law was finally accepted for review, OCHA-Angola established working groups, which included senior technical staff from eleven Ministries and Departments, to finalise operational guidance that would become the law’s supporting regulamento.  The rule of thumb for these groups was to identify an Angolan standard and if it existed, then to write it into the draft regulamento.  In the absence of a national standard, SPHERE provided the default.

- Fifth and finally, as part of their involvement in protection work (see below), OCHA-Angola staff from Luanda, accompanied by legal staff from the National Police and the military, as well as officials from the Attorney General’s Office and the Ministry of Social Affairs, undertook a series of protection workshops in the provinces to promote the importance of protecting civilians.  These workshops developed operational guidance for protection that was based on the Guiding Principles.

- Throughout the process, Government cooperation was maintained partly through the implicit leverage wielded by the humanitarian community.  Resettlement would take place -- that was a military and political reality.  But Government needed humanitarian organizations to assist the resettled if they were to avoid perpetrating a completely pernicious act of violence against their own people.  There were also elements within the Government who understood their moral and legal obligations to the resettled.  The end result was that the Norms passed into Law on 5 January 2001.

- Having already developed the regulamento (see paragraph 29), OCHA-Angola introduced them into ongoing planning processes at the same time as they were being reviewed by the Government.  The regulamento were approved by Government and made official on 23 December 2002.  In the intervening months they had become the accepted standard within the humanitarian community.

- OCHA-Angola’s greatest challenges throughout this process may have been those created by the Government of Angola, which exhibited all the characteristics associated with the Administration of a failing state: dysfunction, limited accountability, lack of transparency or consistency of policy, and limited human resources.  These shortcomings created delays, frustration and at some moments threatened the success of the process.  OCHA-Angola addressed these challenges by forming coalitions with “sympathetic” officials (most technical, some political), and by pursuing other opportunities to strengthen overall relations with Government.  Establishment of the Norms and regulamento is an example of the benefits and challenges of considered and sustained relations with Government during a complex emergency.

- Deference to the Norms and regulamento in Angola is remarkable.  Nearly three years after being passed into law, they are a regular reference and touchstone for Government officials, UN Agency and NGOs -- in the Luanda and in the provinces.

ii. Protection – OCHA can participate directly in protection work when they have a clear comparative advantage to do so.

Summary

- The need for protection of civilians, and of the internally displaced in particular, was an ongoing requirement of the conflict in Angola.  In response to an especially intense period of displacement, the UN Humanitarian Coordinator tasked OCHA-Angola and UNHCR with addressing protection requirements of war affected civilians.  OCHA-Angola’s involvement was based on their capacity and value added – both in terms of their network of field offices, and their advocacy impact in Luanda.

- In early 2000 UNITA changed war tactics for the last time when the movement’s leader instructed his military commanders to revert to guerrilla tactics and to cease communications with central command.  This directive, combined with the Government’s intention to displace civilians as a war-tactic, created an expectation within the humanitarian community that the displacement on both sides would increase.  This expectation was confirmed by events.

- The obligation of the United Nations to address the protection needs of these displaced was emphasized by the Deputy Emergency Relief Coordinator during a March 2000 mission to Angola.  In response and pursuant to IASC Guidelines on the matter, the UN Humanitarian Coordinator directed OCHA-Angola and the Angola office of the United Nations High Commissioner for Refugees (UNHCR) to convene a group to develop a strategy for improving protection of the displaced.   That strategy had four components:  information monitoring, advocacy and response, capacity building and community mobilization.

- OCHA-Angola’s involvement in IDP-protection was based partly on its strengths (field presence, information network and links to Government) and partly on the weaknesses of the rest of the system.  For example, the UN Human Rights presence in Angola did not have the capacity to engage in the operational elements of protection work, nor did they have a mandate to work outside Luanda.  Similarly, though UNHCR participated in development of the protection strategy, operational limitations prevented them from implementing any of its proposed actions.

- OCHA-Angola implemented the first two elements of the strategy: information monitoring, and advocacy and response.  To prepare staff for their additional responsibilities, OCHA-Angola commissioned the ICRC to train Field Advisers in some elements of protection work, focusing on the interview and information gathering techniques.  The training emphasized management of the delicate balance between building a powerful advocacy case, and preserving the confidentiality of a source or sources.  In a complementary measure, OCHA-Angola staff from Luanda toured the provinces, with officials from a number of Government services, departments and ministries, departments and Government services (see paragraph 34), to stress the importance of the protection of civilians.

- In carrying out protection work, the obligations of OCHA-Angola field staff were strictly proscribed.  They were instructed to investigate three situations: instances of forced displacement, instances of forced return, and violations of civil and political rights.  To further reduce OCHA-Angola’s Field Advisers’ exposure to risk strict limits were also set for provincial or field level advocacy.  It could only be undertaken directly when the Norms and regulamento were being violated, or when humanitarian personnel or materials were being abused.  All other cases were triangulated up to Luanda.

- Field Coordinators’ views on performing protection work varied.  A minority believed that coordination and protection responsibilities were incompatible.  This group felt that protection obligations created a second agenda that undermined relations with local authorities and distracted from coordination of assistance.  The majority however, saw the protection work as a complement to their own coordination work.  Any possible conflict of priorities between protection and coordination work was approached with utilitarian pragmatism and resolved in favour of whichever activity had greater “life-saving” impact.  Most Field Advisers also believed that they were obliged, in the absence of any credible alternative, to become engaged in protection.

iii. The Emergency Response Fund – A transparently managed, uncomplicated quick disbursement fund is a highly effective means of meeting emergency needs and maintaining the momentum of a wider humanitarian strategy.

Summary

- OCHA-Angola was entrusted by donors to manage a catalytic fund used to support NGOs to carry-out emergency activities.  The fund was a success because it had something to offer to all concerned.  The donors saw their money disbursed rapidly with minimal overhead extracted.  The NGOs received funding quickly for work time sensitive work and OCHA-Angola was able to support activities that were consistent with agreed priorities.

Detail

- In 1997 three donors provided funding to the OCHA-Angola to disburse to humanitarian organisations undertaking emergency activities.  This total value of the rapid funding mechanism increased over time, peaking in 2002 at just under eight million American dollars.  This “Emergency Response Fund” (ERF) was formally administered by OCHA-Geneva and by 2000 provided funding of not more than $130,000 for emergency projects of 6 months duration or less.  All funding was granted based on the recommendation of OCHA-Angola.

- Partner organisations, and NGOs in particular, appreciated a mechanism that allowed them to react quickly by designing and implementing emergency activities based on their preferred methods and approaches.  Partners also appreciated the transparency of the application, approval and monitoring processes.  Although it is noteworthy that truancy of reporting has become a problem in management of the ERF.

- Donors put great stock in a mechanism that could support activities on very short notice.  This allowed slower but more substantial funding to come on track with little or no delay-related opportunity cost.  Donors’ trust in the mechanism has been such that earmarking has occurred only very rarely.

- For both constituencies the ERF was seen as an “enabling” mechanism – as a provider of start-up funding to initiate essential work quickly or bridge funding to continue essential work while inevitable bureaucratic blockages were unraveled.

- The ERF also gave teeth to the idea that the humanitarian community as a whole would agree on priorities in a coordinated fashion.  NGOs who showed themselves able to respond to agreed priorities knew there was the possibility that start-up funds would be available via the ERF.

- In the early stages UN Agencies believed the ERF to be undermining their efforts at safeguarding the technical integrity of their sector of concern.  They objected to OCHA agreeing to fund NGO activities without first consulting them.  This created the perception among some UN Agencies that OCHA-Angola was diminishing NGO accountability to the UN’s technical agencies and creating a separate humanitarian programme.  This misgiving was addressed by the introduction of a review process that requires ERF proposals to be cleared by the relevant UN Agency prior to their being funded.

iv. Leadership - “Full” Coordination requires high quality leadership that is committed to the humanitarian imperative.

Summary

- OCHA-Angola would not have realized its ambitious plans without superlative leadership.  The UN Humanitarian Coordinator took consistently strong positions on the humanitarian imperative with the Government, the UN family and the wider humanitarian community.  The Head of Office combined a highly centralized approach to internal management with an activism in external relationships.  These two individuals combined to drive OCHA’s work over the review period.

Detail

- Effective management of information was one of the hallmarks of OCHA-Angola leadership.  No outputs left the office without being reviewed and often revised by the Head of Office.  Similarly, benefiting from the positions of the UN Humanitarian Coordinator and the Head of Office on the UNCT and their links to both the Government and diplomatic corps, they kept humanitarian partners informed of relevant political developments.  This regular sharing of “intelligence” and useful analysis was a regular reminder of the utility of a well-informed coordination office working to serve the wider community.

- Planning processes were managed with equal rigor.  Throughout the complex series of meetings, workshops and informal discussions that constituted the humanitarian planning process (see section C.) the Head of Office tailored consistent and complementary messages for different audiences.  As a result all major elements of a diverse constituency were made to understand the benefits of shared strategy.  The Head of Office also identified a hierarchy of partners within OCHA-Angola’s constituency and undertook special efforts to ensure the “buy-in” of the most influential among them (see paragraph 9).

- Assertive management and high-profile external relations come with risk.  Shortcomings, perhaps even more than successes are going to be ascribed to a strong leader who endeavoured to be involved in all substantive work of the coordination office to some level of detail.  Some of the associated risks were mitigated by the close collaboration between the UN Humanitarian Coordinator and the Head of Office.  The Humanitarian Coordinator endorsed the ideas and plans generated by OCHA-Angola within UN family discussions.  He also argued the humanitarian case as strongly as was required with the Government.  This support from the HC was an essential element of maintaining the momentum of humanitarian coordination.

- The quality of staff within OCHA-Angola also contributed directly to the achieving the office’s goals.  Senior staff all possessed extensive experience in Angola, were accustomed to working in a protracted crisis, and had complete facility with Portuguese.  It is also noteworthy that senior staff within OCHA-Angola all possessed considerable organizing skills and a familiarity with the modus operandi of the quasi-Marxist Government of Angola.

E. Conclusion – The Principal Lesson of Angola

There is an implicit requirement in all protracted, complex emergencies for “full coordination.”

- OCHA-Angola applied effective information management, an inclusive planning process, an extensive field network and leadership of great competence to implement “full coordination.”   These four elements and the approaches and techniques described above enabled OCHA-Angola and partners to agree on goals and priorities, increase the efficiency of the total humanitarian operation and leverage their unity to create change in Government policy.  These achievements would not have been possible without the astute activism of OCHA-Angola’s “full coordination.”

- This lesson can be applied to other cases.  If made to function, the wider community will support “full coordination.” Donors will fund it and give it their political support, seeing its clear value added and labour saving effect in the areas of reporting, monitoring and quick disbursement funding.  UN Agencies and NGOs will embrace it, realising the multiplier effect it can have on their work by making them part of larger, unified community.  Government will have to address it, given the importance of humanitarian assistance in most protracted crises.

- Environmental considerations are also a factor in the implementation of “full coordination.”  This approach will likely have its best chance of working where there is an internationally recognised Government labouring under certain resource constraints, a small number of influential donors, a UN family with limited operational capacity and long-term NGO presence.

- “Full coordination” is a high-risk proposition.  With leadership comes exposure to criticism.  While some can be addressed and resolved, some (particularly from the Government, or a particularly discontented UN Agency) can be prohibitive.  There is also the inevitable risk of mission creep.  Effective performance begets requests for involvement in new areas.  OCHA-Angola filled significant gaps regularly.  Some of this activity was alleged to have been operational.  Deciding whether or not to accept additional responsibilities requires organisational discipline, and a field-based weighing of the real costs and benefits for beneficiaries.  The impact of an expansive approach to coordination can also be seen as activities wind down and exit strategies are developed.  The more the humanitarian coordinators have done, the more the community is dependent on them and the less willing they will be to see the humanitarian coordinators leave.

- Perhaps the final lesson of OCHA-Angola 2000-2002 is that the blueprint for full coordination is well established.  When considered in its totality, the corporate guidance available for field level coordination activities is formidable.  OCHA-Angola, in its own view, invented nothing.  They simply implemented what is called for in standing global guidelines.  While this is an understatement, it begs the question regarding approaches to coordination being taken in other protracted complex crises.

*****

Annex 1 –Terms of Reference

OCHA in Angola – Innovations in Coordination

Lessons Learning Review

# Background

- For many years, Angola was one of the most challenging humanitarian crises in the world, characterized by massive displacement, hundreds of thousands of civilian deaths, egregious violations of human rights, complete destruction of infrastructure, and a huge landmine problem.  In response, the UN and other humanitarian organizations mounted a large and logistically complex operation involving more than 10 UN agencies, 80 international NGOs and 3000 national NGOs.

- The crisis took a dramatic turn in February 2002 with the death of the UNITA rebel leader Jonas Savimbi.  His death led to a cessation of hostilities agreement, the cantonment of UNITA troops and their family members, and the opening of the hitherto inaccessible areas to humanitarian organizations.  During 2002, the humanitarian assistance community in Angola mobilised a massive relief effort to provide life-saving support to approximately 2,000,000 Angolans.  This period of intense humanitarian activity took place was driven by increased access to needy populations following the end of the conflict.  It is widely recognised that successful implementation of relief operations during this period was partly a function of coordination and prioritization efforts provided by the UN Humanitarian Coordinator and his colleagues in the OCHA office in Angola.  This coordination, sometimes characterized as “full” coordination, required major humanitarian actors to work in extremely close collaboration in the delivery of critical relief materials across the country.

- The intense, life-saving work carried out in the summer of 2002 came at the end of a two year period that saw OCHA Angola undertake a number of innovative actions, including the adoption of the Guiding Principles on IDPs into Angolan law, the creation of a number of information management systems, the development of the Emergency Response Fund (ERF), and OCHA’s active involvement in protection matters.

- The achievements of OCHA Angola during the period 2000-2002 were built upon eight years of OCHA presence in-country. Over the course of this relatively long life span, OCHA Angola developed noteworthy characteristics, including an extensive field presence, the aforementioned ERF, and an elaborate array of planning mechanisms (e.g. meetings and planning groups).  Given the end of the conflict and a receding of humanitarian needs, OCHA is developing an exit strategy to allow it to leave Angola.

# Purpose and Scope of Review

- The purpose of this review is to capture the lessons of “full coordination” in order to identify its benefits, its costs and the pre-requisites (both environmental and OCHA-specific) for its application.  To that end and in this context, the study will be limited to a review of the period 2000-2002, inclusive.

# Key Issues to be Addressed

- What were the principal components of humanitarian coordination in Angola during the period in question and how did they function, with specific reference to:

  - Planning Tools

    - to what degree was planning inclusive (with whom did it occur)?

    - to what degree was planning strategic in setting goals & objectives for the wider humanitarian community?

  - Assessment Tools

  - Plans of Action and Response

  - “Core Pipelines” Concept

  - Monitoring

  - Relationship between UN HC and OCHA, and between UN HC and the UN Country Team

  - Coordination Mechanisms

  - Field Presence

  - Information Management

  - Support Services

  - Protection

  - Advocacy

  - Emergency Response Fund

  - Resource Mobilisation

  - Financial and Administrative Management

This section should also describe the capacity of the Government at the central and provincial levels, as well as the capacity of national and international humanitarian partners.

- To what degree are these principal components replicable in other settings?  What aspects of this approach are the most important?  What steps can OCHA take to replicate the most important components?

- What was the result of humanitarian of coordination in Angola during the period in question, with specific reference to:

  - Drafting of strategic frameworks including the Appeal

  - Prioritisation of humanitarian activities

  - Needs assessments

  - Plans of action and the timely provision of emergency assistance

  - Delivery of core pipelines

  - Normative innovations (e.g. facilitating the introduction of new laws related to IDP norms).

  - Resource mobilisation

  - Advocacy

Methodology

- As defined by OCHA’s evaluation framework, the lesson learning review is an internal review and as such will focus on contributing to and facilitating organizational learning.  The main method used will be semi-structured interviews of key informants and at headquarters.

- A desk review of information/documentation provided by OCHA Geneva

- Semi-structured interviews of relevant units within OCHA headquarters;

- Semi-structured interviews of senior and technical representatives of the UN agencies in Angola.

- Semi-structured interviews of other partners on the ground in Angola, e.g. 1. NGOs, 2. Red Cross, 3. Bilateral donor Governments, 4. Multilateral donors.

- Semi-structured interviews with representatives of the Government of Angola.

- Semi-structured interviews with members of the Angola OCHA team.

- A possible lessons workshop in Luanda with partners including Government representatives.

Reporting Requirements and Processes:

- A first draft report should be submitted at the latest three weeks after return of the team from the field.  The report should be no longer than 5,000 words, including a succinct 500 word summary and will be written in English.  The first draft will be shared with key stakeholders in the field and in agency HQ and comments and inputs will be reflected in the final report to be submitted three weeks after receipt of the first draft.

Team Composition

- The review team will consist of one external consultant with appropriate experience and one OCHA staff member.

Timeframe

- The overall duration of this review will be five weeks, including one week in Angola, one week for the desk review, one week for HQ interviews and interviews of key informants no longer in Angola and two weeks for report writing.

Management and Organization

- Overall co-ordination for the study, as well as administrative support, lies with the OCHA’s Policy Development and Studies Branch/ Evaluation and Studies Unit.

- Relevant units of OCHA Geneva and New York will provide the Study team with background information and documentation as required, as well as guidance in the practical conduct of the Study (partners on the ground to be interviewed, advice on the OCHA’s standard procedures for Disaster Response, etc.).

# Use of Review

- The review will both be used at a general as well as at a more specific level, i.e. to assess the replicability of the "full" coordination model and to provide input to the exit strategy.  It is expected that some of the reviews findings will have impact on OCHA’s global policy.  To that end, results will be presented to key stakeholders.

Annex 2 – Respondents

Name						Function

| Advirta, | Rosario* | OXFAM International |
| --- | --- | --- |
| Arroyo, | Fernando | Field Adviser, OCHA Angola |
| Balthazar, | Manuela* | FONGA |
| Barnes, | Holly* | SC-UK |
| Benoit, | Elise | Programme Officer, WFP Angola |
| Beraki, | Matewos | Programme Officer, UNHCR Angola |
| Blaylock, | Dawn | Information Officer, OCHA Angola |
| Bosco, | Giovanni | Policy Advisor, OCHA Angola |
| Brinks, | H.E. Robert Gerard | Ambassador, Government of the Netherlands |
| Bulten, | Robert Jan | Asst. Country Director CARE Int’ll Angola |
| Cabrera, | Ana Grace* | UNHCR |
| Carosi, | Paola | Head of Unit a.i., OCHA Angola |
| Chricboom, | Christian | Field Coordinator, OCHA Angola |
| Cochat, | Vera | NGO/ERF Unit, OCHA Angola |
| Conway, | James | OFDA Officer, USAID Angola |
| Cordeiro, | Luis Augusto* | ADRA Nacional |
| Dive, | Phillip | Field Adviser, OCHA Angola |
| Domingos, | Nsala* | World Health Organisation |
| Dontaine, | Jean-Francois | Agronomist, FAO Angola |
| Endresen, | Gunvor Elida | Counsel, Norwegian Embassy |
| Falcone, | Marco | Agronomist, FAO Angola |
| Ferrari, | Mario | UNICEF Rep. And UNRC/HC a.i. |
| Flatin, | Anne Lizette | Second Secretary, Norwegian Embassy |
| Gjerdrum, | Cecilia | Counsel, Swedish Embassy, Angola |
| Goñcalves, | Pedro | Field Adviser, OCHA Angola |
| Hellyer, | Robert | Mission Director, USAID Angola |
| Johnson, | Martin | Representative, DFID |
| Kinloch, | Stephen | Programme Manager, UNDP Angola |
| Langvik, | Sigbjorn* | Norwegian Peoples Aid |
| Leite da Costa, | Dr. Julio | Asst. Representative, UNFPA |
| Lopes, | Claudio | Field Adviser, OCHA Angola |
| Luna, | Ricardo | Administrator, FAO Angola |
| Martin, | Andrew | Field Adviser, OCHA Angola |
| Martins, | José Antonio | Principal Advisor, MINARS |
| McDonald, | Iain | Head of Programme Section, WFP Angola |
| Mobilia, | Rogerio | ISS Unit, OCHA Angola |
| Morelli | Ginelli | Field Adviser, OCHA Angola |
| Moussa, | Sylla | Transport Consultant, OCHA Angola |
| Murray, | George | Field Adviser, OCHA Angola |
| Naik, | Prasant* | OXFAM GB |
| Neto, | Gaspar | Vice Governor, Malange |
| Neves, | Joao | Programme Director, SC-UK |
| Olson, | Maria | ECHO Representative, Angola |
| Paulo, | Vincente* | FONGA |
| Popp, | Milena | Field Adviser, OCHA Angola |
| Quinta, | Justino* | FONGA |
| Rasmussen, | Christina* | Lutheran World Federation |
| Raya, | Luis | Field Adviser, OCHA Angola |
| Redmond, | Christian* | Halo Trust |
| Schmid, | Alain | Chief of Delegation |
| Serres Pires, | José | Field Adviser, OCHA Angola |
| Stavrou, | Vivi* | CCF |
| Steen-Nilsen, | Aksel* | Norwegian Peoples Aid |
| Tantaruna, | Luz* | IOM |
| Thompson, | Julie | Information Officer, OCHA Angola |
| Vander Espt, | Pascale | Consultant, UN Human Rights Division |
| Victor, | Antonia* | UTCAH |
| Zaccagnini, | Carlos | Deputy Representative, UNHCR |

* Workshop Participants.

N.B. – Respondents list does not include those interviewed in Malange.

This report reflects the view of its author and does not represent the official position of the UN Office for the Coordination of Humanitarian Affairs.

In 2002 alone 2 million Angolans required life saving assistance.

The civil war was preceded by 13 years of internal anti-colonial conflict.  It ended with the signing of the Luena Memorandum of Understanding in April 2002 by the Government of Angola and the National Union for the Total Independence of Angola (UNITA).

In 1993 the UN Department of Humanitarian Affairs – OCHA’s direct antecedent – established an office in Angola.

Research in Angola included a four-day mission to Malange, and culminated with a workshop discussion in Luanda, which included representatives from the Government, the UN Agencies and Programmes and International and National NGOs. This review was undertaken by Michael Gaouette, an OCHA staff member.

This Lessons Learned report will not reflect the ‘how to’ details of OCHA Angola’s work.  That is a separate and more detailed exercise that is referenced in paragraph 4.

Pursuant to internal guidelines, OCHA’s Lessons Learned are based on the experiences of  “…those who have…implemented an activity…”  (‘Draft Concept and Guidelines OCHA Lessons Learned Review,’ OCHA/PDSB/ESU 2002).  As such, they are meant to reflect the views of OCHA staff regarding areas of importance, achievement and significant challenge during the period under review.  It is an inevitable weakness of this approach that critical feedback is exceptional.

In some cases collaboration on assessments was remarkable -- a multi-sectoral and multi-agency team would often conclude a rapid assessment by carrying out a MUAC survey on behalf of nutritional agencies, using guidelines from the common assessment protocol.  This is an extraordinary level of collaboration, where the usual issues of ‘ownership’ of sectors and the reluctance to dedicate staff time to the work of other organizations seem to have been overcome.

During particular fluid periods of the crisis, when mass displacement occurred rapidly and emergency responses were required, assessments findings became the basis for Emergency Plans of Action

Details of these assessment protocols (RACN and ISMT) are available from the OCHA-Angola Office.

This characterisation applies to the 2001-2003 post-holder only.

A regular bulletin titled The Humanitarian Coordinator’s Update was an example of this sort of analytical output.

This support for National NGOs was consistent with OCHA-Angola’s inclusion of capacity building in most of their work

A minority of OCHA-Angola Field Advisers believed that security-related responsibilities did represent a conflict of interest and distracted from coordination work.  The majority, however, saw it as complementary and another tool at their disposal to support humanitarian operators.

Separation of families and sexual violence was widespread during this displacement.

This is despite the fact the article 21 of the Angolan constitution calls for adherence to all international treaties and agreements signed by the Government.  Angola is a signatory to the UN Convention on Human Rights and the UN Convention on the Rights of the Child, among others.

There was a serious divergence of views among humanitarian actors on this approach.  One NGO alleged that the “principles of engagement” aided forced resettlement.

There were also instances of SPHERE standards being altered to suit the Angolan context (in water and sanitation for example, regarding daily water requirements, which the regulamento set well below the SPHERE Standards).

During the course of research for this paper (in August 2003) in a small village in Malanje province, the WFP Chief of Sub-Office energetically challenged local officials on their adherence to the norms.

This tidy explanation does not reflect the “mandate envy” that characterized the UN Human Rights/OCHA-Angola discussions on protection.  UN Human Rights staff believed they could have played a greater role if allowed.  OCHA-Angola contends that they did not have the capacity to do so.

It should be noted that OCHA-Angola Field Advisers had already received training in the basic components of International Humanitarian Law as a separate matter.

Maximum grant amount grew over the years.  Initially the amount was $50,000.  That grew to $100,000 in 1998 and again to $130,000 ($200,000 in exceptional cases) in 2000.

The ERF had an antecedent.  In 1995 the United Nations Office for Humanitarian Coordination in Angola (UCAH) managed an NGO fund based on a similar approach.  The fund had lapsed somewhat when the ERF was established.

In contrast to the frequent fate of NGOs, which sees them as the unthinking implementers of UN Agency designed or identified activities

ERF overhead is 3%.

OCHA-Angola reports that in some cases this has slowed the process prohibitively, making the approval process meaningless.

In Angola WFP was far and away the dominant operational agency within the UN family.  Their transport and logistics capacity was the backbone for much of the humanitarian operation.  The relative capacity of the other UN Agencies and Funds made them sensitive to the benefits of collaboration.

For example, OCHA-Angola designed and managed the agricultural distribution plan in 2000-2001 and 2001-2002.

This guidance would include the Humanitarian Coordinator’s Terms of Reference, the Field Guidelines issues by OCHA, directives on the CAP and the CHAP and the myriad other sets of instructions and requirements that have been generated on field level coordination.

Including the UN Charter.

In 1994 a field presence for the UN Department of Humanitarian Affairs was established in Angola.